## Process Plan 2026_27
ANNEXURE A (This Time Schedule was drafted in accordance with Section 21(1)(b) of the Local Government: Municipal Finance Management Act, No. 56 of 2003 and Section 34 of the Local Government: Municipal Systems Act, No. 32 of 2000 and supporting Regulations of both Acts) |  |  |  | LIST OF ACRONYMS IDP: Integrated Development Plan PM: Performance Management SDF: Spatial Development Framework DBMLUP: Drakenstein Bylaw on Municipal Land Use Planning
Time Schedule to Review, Compile and Finalise the IDP, BUDGET, PM and SDF for 2027/28
ACTIVITY/TASK |  | LEGISLATIVE REQUIREMENTS | TARGET DATES |  |  |  |  | RESPONSIBLE OFFICIAL
NO | DESCRIPTION |  | IDP | BUDGET | PM | SDF | REPORTING
JULY 2026
1 | Make public the projections, targets and indicators as set out in the SDBIP (no later than 14 days after the approval of the SDBIP) and submit to National and Provincial Treasuries (no later than 10 days after the approval of the SDBIP) | MFMA - Sec 53(3)(a) MBRR - Reg 20(2)(b) |  |  | 01/07/2026 |  |  | Head: Strategic Performance Management and M&E
2 | Commence with the preparation of the 2026/2027 Roll Over Adjustments Budget | MFMA - Sec 28(2)(e) MBRR - Reg 23(5) |  | 06/07/2026 |  |  |  | Manager: Budget Control and Cost Accounting
3 | Submit Monthly report on the budget for period ending 30 June 2026 within 10 working days to Executive Mayor | MFMA - Sec 71(1) |  |  |  |  | 14/07/2026 | Manager: Financial Statements, Reporting and Cash Management
4 | Quarter 4 (2025/2026) Performance Assessments for City Manager, Executive Directors and Reporting Level 3 Managers | MPPMR - Reg 13 GN 21- 17/01/2014 |  |  | 15/07/2026, 16/07/2026 |  |  | Head: Strategic Performance Management and M&E
5 | Submit 2025/2026 Fourth Quarter Performance Report to Council | MPPMR - Reg 13 MFMA - Sec 71(1) |  |  | 28/07/2026 |  |  | Head: Strategic Performance Management and M&E
6 | Submit Quarterly report for period ending 30/06/2026 on implementation of the budget and financial state of affairs of the municipality to Council | MFMA - Sec 52(d) MFMA - Sec 71(1) MBRR - Reg 29 |  |  |  |  | 29/07/2026 | Manager: Financial Statements, Reporting and Cash Management
7 | Supply Chain Management - BEC and BAC Meetings | [6 empty] | All HODs
AUGUST 2026
8 | Place 2025/2026 Fourth Quarter Performance Report on website | MFMA - Section 75 (2) MSA 21(b) |  |  | 03/08/2026 |  |  | Head: Strategic Performance Management and M&E
9 | Submit 4th Quarter (2025/2026) Performance Reports - SDBIP Performance Reports to National and Provincial Treasuries | MPPMR - Reg 13 |  |  | 03/08/2026 |  |  | Head: Strategic Performance Management and M&E
10 | Budget Steering Committee considers the 2026/2027 Roll Over Adjustments Budget | MFMA - Sec 28 MBRR - Part 4 |  | 12/08/2026 |  |  |  | Manager: Budget Control and Cost Accounting Manager: IDP/R&D
11 | Submit Monthly report on the budget for period ending 31 July 2026 within 10 working days to Executive Mayor | MFMA Section 71(1) |  |  |  |  | 14/08/2026 | Manager: Financial Statements, Reporting and Cash Management
12 | Submit 1st Draft AR and progress report to SMT for discussion | [5 empty] | 17/08/2026 | Financial Planning and Accounting Analyst / Administrative Support Officer
13 | Submit 2nd Draft AR 2025/2026 to SMT for review; this will include a review on quality assurance and that submitted information is valid, accurate and complete | Not Applicable |  |  |  |  | 21/08/2026 | Financial Planning and Accounting Analyst / Administrative Support Officer
14 | Finance Portfolio Committee recommends 2026/2027 Roll Over Adjustments Budget to Executive Mayor and Mayoral Committee | MFMA - Sec 28(2)(e) MBRR - Reg 23(5) |  | 19/08/2026 |  |  |  | Chief Financial Officer
15 | Executive Mayor and Mayoral Committee approve 2026/2027 Roll Over Adjustments Budget | MFMA - Sec 28(2)(e) MBRR - Reg 23(5) |  | 19/08/2026 |  |  |  | Chief Financial Officer
16 | Council approve 2026/2027 Roll Over Adjustments Budget (to be tabled before 25 August 2026) | MFMA - Sec 28(2)(e) MBRR - Reg 23(5) |  | 25/08/2026 |  |  |  | Chief Financial Officer
17 | Executive Mayor and Mayoral Committee recommend that Budget/IDP/PM/SDF Process Plan (at least 10 months before the start of the budget year) | MFMA - Sec 21(1)(b) | 25/08/2026 | 25/08/2026 | 25/08/2026 | 25/08/2026 |  | Manager: IDP/R&D
18 | Submit Annual Performance Report (APR) and Annual Financial Statements (AFS) for 2025/2026 to the Auditor General of South Africa (AGSA) | MFMA - Section 126 |  |  | 31/08/2026 |  | 31/08/2026 | Head: Strategic Performance Management and M&E CFO
19 | Supply Chain Management - BEC and BAC Meetings | [6 empty] | All HODs
20 | Publish notice in the press regarding the intention to compile a SDF and to inform the public of the process that will be followed | DBMLUP - Sec 3(2)(a) |  |  |  | 28/08/2026 |  | Manager: Spatial Planning
21 | Infrom the Provincial Minister of the intention to compile a SDF | DBMLUP - Sec 3(2)(b) |  |  |  | 28/08/2026 |  | Manager: Spatial Planning
22 | Invite written nominations from organs of state to serve on the Intergovernmental Steering Committee for the compilation of the SDF | DBMLUP - Sec 5(2) |  |  |  | 28/08/2026 |  | Manager: Spatial Planning
SEPTEMBER 2026
23 | Submit the adopted Budget/IDP/PM/SDF Time Schedule to the MEC for Local Government and Provincial Treasury | MSA - Sec 21, 21A, 28(3) | 30/08/2026 |  |  | 30/08/2026 |  | Manager: IDP/R&D
24 | Place advertisement to notify the public of the approved Budget/IDP/PM/SDF Process Plan on website, local newspapers and notice boards | MSA - Sec 21, 21A, 28(3) | 30/08/2026 |  |  |  |  | Manager: IDP/R&D
25 | Submit Monthly Report on the Budget for period ending 31 August 2026 within 10 working days to Executive Mayor | MFMA Section 71(1) |  |  |  |  | 14/09/2026 | Manager: Financial Statements, Reporting and Cash Management
26 | Register relevant stakeholders who must be invited to comment on the draft SDF | DBMLUP - Sec 3(2)(c) |  |  |  | 21/09/2026 |  | Manager: Spatial Planning
27 | Budget Steering Committee determines Budget Assumptions (Parameters) for 2026/2031 Medium Term Revenue and Expenditure Framework (MTREF) Budget: - Assumptions - Tariffs - HR/Staff Costs - Events - Bursaries - Related policy amendments - Capital expenditure (loans) | MFMA - Sec 28 MBRR - Part 4 | [5 empty] | CFO
28 | Review of Departmental Sector Plans: Disaster Management Plan, Sector Plans |  | 30/09/2026 |  |  |  |  | All HODs
29 | Provincial IDP Managers' Forum | MSA Section 24 | 30/09/2026 |  |  |  |  | Manager: IDP/R&D
30 | Supply Chain Management - BEC and BAC Meetings | [6 empty] | All HODs
OCTOBER 2026
31 | Compile a draft Status Quo Report for the SDF and refer the draft document to the Intergovernmental Steering Committee for comments | DBMLUP - Sec 6(1) |  |  |  | 2026-01-10 |  | Manager: Spatial Planning
32 | Request and receive inputs from departments for 2026/2027 Adjustments Budget and the 2027/2032 Draft MTREF | MFMA - Section 21 & 28 | [5 empty] | All Departments
33 | Submit Monthly report on the budget for period ending 30 September 2026 within 10 working days to Executive Mayor | MFMA Section 71(1) |  |  |  |  | 14/10/2026 | Manager: Financial Statements, Reporting and Cash Management
34 | Quarter 1 (2026/2027) Performance Assessments for City Manager, Executive Directors and Reporting Level 3 Managers | MPPMR - Reg 13 GN 21- 17/01/2014 |  |  | 14/10/26 - 15/10/26 |  |  | Head: Strategic Performance Management and M&E
35 | Submit 2026/2027 First Quarter Performance Report to Mayoral Committee | MPPMR - Reg 13 |  |  | 30/10/2026 |  |  | Head: Strategic Performance Management and M&E
36 | Submit 2026/2027 First Quarter Performance Report to Council | MPPMR - Reg 13 |  |  | 30/10/2026 |  |  | Head: Strategic Performance Management and M&E
37 | Submit Quarterly report for period ending 30/09/2026 on implementation of the budget and financial state of affairs of the municipality | MFMA - Sec 52(d) MFMA - Sec 71(1) MBRR - Reg 29 |  |  |  |  | 28/10/2026 | Manager: Financial Statements, Reporting and Cash Management
38 | Request tariff inputs from departments to be included in tariff book. | MFMA - Chapter 4 MBRR - Part 3 |  | 23/10/2026 |  |  |  | Manager: Budget Control and Cost Accounting
39 | Assess and identify information from adopted Sector Plans for integration into the draft 2026/2026 IDP document if possible | MSA Section 34 | 31/10/2026 |  |  |  |  | Manager: IDP/R&D together with All Departments
40 | Start process to review or amend current budget related policies and develop new budget related policies as needed. | MFMA - Sec 21 MBRR - Part 3 |  | 30/10/2026 |  |  |  | Manager: Budget Control and Cost Accounting
41 | Review of Policies and Bylaws | [6 empty] | All EDs
42 | Macro Structure Review | [6 empty] | All EDs
43 | EPWP Priorities | [6 empty] | All EDs
44 | Supply Chain Management - BEC and BAC Meetings | [6 empty] | All HODs
NOVEMBER 2026
45 | Local Government Elections |  | 04/11/2026 | 04/11/2026 | 04/11/2026 | 04/11/2026 | 04/11/2026
46 | Submit 1st Quarter 2026/2027 Performance Reports - SDBIP and Finance Performance Reports to National and Provincial Treasury |  |  |  | 01/11/2026 |  |  | Head: Strategic Performance Management and M&E
47 | Place 2026/2027 First Quarter Performance Report on website | MFMA - Sec 75(2) MSA - Sec 21(b) |  |  | 01/11/2026 |  |  | Head: Strategic Performance Management and M&E
48 | Budget Assessment Team (BAT) sessions to prioritise projects and motivate budget requests. |  |  | 09/11/2026 to 20/11/2026 |  |  |  | Chief Financial Officer
49 | Consider comments from the Intergovernmental Steering Committee and finalise the Status Quo | DBMLUP - Sec 6(2) |  |  |  | 13/11/2026 |  | Manager: Spatial Planning
50 | Compile first draft SDF and refer to the Intergovernmental Steering Committee for comments. | DBMLUP - Sec 6(3) |  |  |  | 13/11/2026 |  | Manager: Spatial Planning
51 | Prepare 5- Year IDP Process Plan for approval by the newly elected Council in order to be advertised for public participation. | MFMA - Sec 75(2) MSA - Sec 21(b) | 30/11/2026 |  |  |  |  | Manager: IDP and Research & Development
52 | April Public Participation Preparation |  | 30/11/2026 |  |  |  |  | Manager: IDP/R&D
53 | Submit Monthly report on the budget for period ending 31 October 2026 within 10 working days to Executive Mayor | MFMA Section 71(1) |  |  |  |  | 13/11/2026 | Manager: Financial Statements, Reporting and Cash Management
54 | Supply Chain Management - BEC and BAC Meetings | [6 empty] | All HODs
55 | MAAP Processes | [5 empty] | 30/11/2026 | Senior Manager: Budget, Assets and Financial Reporting
DECEMBER 2026
56 | Finalise Draft Tariff Book | MFMA - Sec 21 |  | 2026-04-12 |  |  |  | Manager: Budget Control and Cost Accounting
57 | Provincial IDP Managers' Forum | MSA Section 24 | 02/12/2026 to 04/12/2026 |  |  |  |  | Manager: IDP/R&D
58 | Submit Monthly report on the budget for period ending 30 November 2026 within 10 working days to Executive Mayor | MFMA Section 71(1) |  |  |  |  | 14/12/2026 | Manager: Financial Statements, Reporting and Cash Management
JANUARY 2027
59 | Consider the comments from the Intergovernmental Steering Committee on the first draft SDF and finalise first draft SDF. | DBMLUP - Sec 6(4) |  |  |  | 2027-04-01 |  | Manager: Spatial Planning
60 | Quarter 2 and Mid-Year (2026/27) Performance Assessments for City Manager, Executive Directors and Reporting Level 3 Managers | MPPMR - Reg 13 GN 21- 17/01/2014 |  |  | 14/01/2027 - 15/01/2027 |  |  | Head: Strategic Performance Management and M&E
61 | Submit Monthly report on the Budget for period ending 31 December 2026 within 10 working days to Executive Mayor | MFMA Section 71(1) |  |  |  |  | 14/01/2027 | Manager: Financial Statements, Reporting and Cash Management
62 | Submit Second Quarter Performance Report to Executive Mayor and Mayoral Committee | MPPMR - Reg 13 |  |  | 20/01/2027 |  |  | Head: Strategic Performance Management and M&E
63 | Prepare an agenda item for submission of the 2025/2026 Draft AR to the Finance Portfolio Committee, Mayoral Committee and Council | MFMA - Sec 21 |  |  |  |  | 8/01/2027 | Financial Planning and Accounting Analyst / Administrative Support Officer
64 | Submit Mid-Year Performance Assessment Report to Executive Mayor | MFMA - Sec 72 |  |  | 25/01/2027 |  |  | Head: Strategic Performance Management and M&E
65 | Prepare and submit Mid-Year Budget Assessment Report to Executive Mayor | MFMA - Section 72(1)(b) MBRR - Reg 35 |  | 25/01/2027 |  |  |  | Chief Financial Officer
66 | Submit Mid-Year Budget and Performance Report to Provincial Treasury, National Treasury and Department of Local Government by 25/01/2027 | MFMA - Section 72(1)(b) MBRR - Reg 35 |  | 25/01/2027 | 25/01/2027 |  |  | Head: Strategic Performance Management and M&E CFO
67 | Council consider 2025/2026 Draft Annual Report before advertising it for public comment | MFMA - Sec 127 |  |  |  |  | 28/01/2027 | Financial Planning and Accounting Analyst / Administrative Support Officer
68 | Submit the 5-Year IDP Process Plan to Council for approval | MFMA - Section 75 (2) MSA - Sec 21(b) | 27/01/2027
69 | Submit Quarterly report for period ending 31/12/2026 on implementation of the budget and financial state of affairs of the municipality to Council | MFMA - Sec 52(d) MFMA - Sec 71(1) MBRR - Reg 29 |  |  | 27/01/2027 |  | 28/01/2027 | Chief Financial Officer and Performance Management Officer
70 | Submit Mid-Year Budget and Performance Assessment Reports to Council | MFMA - Section 72(1)(b) MBRR - Reg 35 |  | 27/01/2027 | 27/01/2027 |  |  | Head: Strategic Performance Management and M&E and Senior Manager: Budget, Assets and Financial Reporting
71 | Place 2026/2027 Second Quarter Performance Report on website | MFMA - Section 75 (2) MSA - Sec 21(b) |  |  | 29/01/2027 |  |  | Head: Strategic Performance Management and M&E
72 | Finalise revision of budget related policies and compilation of new budget related policies | MFMA - Sec 21 MBRR - Part 3 |  | 29/01/2027 |  |  |  | Manager: Budget Control and Cost Accounting
73 | Council consider Status Quo Report and first draft SDF for approval to commence with the 60-day public participation process | DBMLUP - Sec 6(4) |  |  |  | 31/01/2027 |  | Manager: Spatial Planning
FEBRUARY 2027
74 | Strategic Risk Review | [5 empty] | 01/02/2026 | Chief Risk Officer
75 | Give notice of the first draft SDF in the Government Gazette and in the media, and invite comments from the public on the first draft SDF | SPLUMA - 20(3) |  |  |  | 2027-04-02 |  | Manager: Spatial Planning
76 | Make public the Mid-Year Budget and Performance Report in the local newspaper and on municipal website | MFMA - Section 75 (2) MSA - Sec 21(b) |  |  | 04/02/2027 |  |  | Manager: IDP/R&D
77 | Budget Steering Committee considers 2026/2027 Adjustments Budget | MFMA - Sec 28 MBRR - Part 4 |  | 11/02/2027 |  |  |  | Chief Financial Officer
78 | Finance Portfolio Committee considers and recommends the 2026/2027 Adjustments Budget to the MAYCO | MFMA - Sec 28 MBRR - Part 4 |  | 16/02/2027 |  |  |  | Manager: Budget Control and Cost Accounting
79 | MAYCO considers and adopts 2026/2026 Adjustments Budget and potentially revised 2026/2027 TL SDBIP | MFMA - Sec 28 MBRR - Part 4 |  | 17/02/2027 | 17/02/2027 |  |  | Manager: Budget Control and Cost Accounting and Head: Strategic Performance Management and M&E
80 | Council considers and adopts 2026/2027 Adjustments Budget and potentially revised 2026/2026 SDBIP | MFMA - Sec 28 MBRR - Part 4 |  | 26/02/2027 |  |  |  | Manager: IDP/R&D and Manager: Budget Control and Cost Accounting
81 | Send the 2025/2026 Draft AR, within five (5) days via e-mail and hard copy to the National Treasury, the Western Cape Department of Local Government, the Western Cape Provincial Treasury and the Auditor General | MFMA - Section 127(5)(b) |  |  |  |  | 01/02/2027 to 05/02/2027 | Financial Planning and Accounting Analyst / Administrative Support Officer
82 | Due date for the public and other stakeholders to render written comments on the 2025/2026 Draft AR | MFMA - Sec 127(5)(a) MSA - Sec 21A |  |  |  |  | 21/02/2027 | Financial Planning and Accounting Analyst / Administrative Support Officer
83 | Submit Monthly report on the budget for period ending 31 January 2027 within 10 working days to Executive Mayor | MFMA Section 71(1) |  |  |  |  | 12/02/2027 | Manager: Financial Statements, Reporting and Cash Management
84 | Technical Integrated Municipal Engagements (TIME) | MSA - Chapter 5 | 28/02/2027 |  |  |  |  | Manager: IDP/R&D
85 | Submit monthly report for period ending 31/01/2027 on implementation of the budget and financial state of affairs of the municipality to Council | MFMA - Sec 71(1) MBRR - Reg 29 |  |  |  |  | 24/02/2027 | Manager: Financial Statements, Reporting and Cash Management
86 | Submit Draft IDP, and 2026/27 SDBIP to Budget/IDP/PM/SDF Steering Committee | Not Applicable | 16/02/2027 |  | 16/02/2027 |  |  | Manager: IDP/R&D Head: Strategic Performance Management and M&E
MARCH 2027
87 | SDBIP - All layers and performance indicator review |  |  |  | 31/03/2027 |  |  | Head: Strategic Performance Management and M&E
88 | Advertise the approved 2026/2027 Adjustments Budget and Revised TL SDBIP for 2026/2027 and submit budget and B Schedules to National Treasury and Provincial Treasury as required per legislation (within 10 working days) | MFMA - Sec 28(7) MSA - Sec 21A MBRR - Part 4 |  | 11/03/2027 | 04/03/2027 |  |  | Manager: Budget Control and Cost Accounting Head: Stratgic Performance and Management and M&E
89 | Draft Procurement Plan |  |  | 12/03/2027 |  |  |  | CFO and All HODs
90 | Submit monthly report on the budget for period ending 28 February 2027 within 10 working days to Executive Mayor | MFMA Section 71(1) |  |  |  |  | 12/03/2027 | Manager: Financial Statements, Reporting and Cash Management
91 | Budget Steering Committee considers 2027/2032 Draft Budget | MFMA - Sec 28 MBRR - Part 4 |  | 12/03/2027 |  |  |  | Chief Financial Officer
92 | Draft Budget captured on Budget Management Module (BMM) |  |  | 15/03/2027 |  |  |  | Manager: Budget Control and Cost Accounting
93 | Prepare an item with the 2025/2026 OR and AR to be tabled at the Finance Portfolio Committee, Mayoral Committee and Council to be reviewed by the City Manager | MFMA - Sec 129 |  |  |  |  | 12/03/2027 | Financial Planning and Accounting Analyst / Administrative Support Officer
94 | Provincial Sector Departments inform municipalities of provincial budgetary allocations | MSA - Chapter 5 | 16/03/2027 |  |  |  |  | Manager: IDP/R&D and Manager: Budget Control and Cost Accounting
95 | Submit draft revised IDP, and 2027/28 SDBIP to Mayco for discussion | Not Applicable | 24/03/2027 |  | 24/03/2027 |  |  | Manager: IDP/R&D Head: Strategic Performance Management and M&E
96 | Council consider 2025/2026 Oversight Report and Annual Report for approval | MFMA - Sec 129 |  |  |  |  | 31/03/2027 | Financial Planning and Accounting Analyst / Administrative Support Officer
97 | Financial Services Portfolio Committee recommends 2027/2032 Draft Budget to the Executive Mayor and Mayoral Committee | MFMA - Sec 16(2) MSA - Sec 25 MBRR - Part 3 |  | 17/03/2027 |  |  |  | Manager: Budget Control and Cost Accounting
98 | Executive Mayor and Mayoral Committee consider 2027/2032 DraftAmended IDP, Budget, and 2027/28 TL SDBIP | MFMA - Sec 16(2) MSA - Sec 25 MBRR - Part 3 | 19/03/2027 | 19/03/2027 | 19/03/2027 |  |  | Manager: IDP/R&D and Manager: Budget Control and Cost Accounting
99 | Council meeting on Draft IDP, Budget, Tariffs, Budget Related Policies and SDBIP (at least 90 days before the start of the budget year) | MFMA - Sec 16(2) MSA - Sec 25 MBRR - Part 3 | 31/03/2027 | 31/03/2027 | 31/03/2027 |  |  | Manager: IDP/R&D Manager: Budget Control and Cost Accounting Head: Strategic Performance Management and M&E
100 | Submit electricity tariff application to NERSA for approval. | Not Applicable |  | 31/03/2027 |  |  |  | Senior Manager: Revenue and Expenditure
101 | Planning for Organised Stakeholder Engagement for 1st week of May |  | 31/03/2027 |  |  |  |  | Manager: IDP/R&D
102 | Supply Chain Management - Specifications and Adverts for June | [6 empty] | All HODs
103 | Advertise the Draft IDP, SDBIP, Budget and other required documents and provide at least 21 days for public comments and submissions | MFMA - Sec 22(a) MSA - Sec 21A MPPMR - Reg 15(3) | 02/04/2027 | 02/04/2027 | 02/04/2027 |  |  | Manager: IDP/R&D Manager: Budget Control and Cost Accounting Head: Strategic Performance Management and M&E
104 | Consider all representation received from the public on the first draft SDF, compile final draft SDF, and refer to Intergovernmental Steering Committee for comments | DBMLUP - Sec 6(5) SPLUMA - Sec 3(c) |  |  |  | 2027-04-08 |  | Manager: Spatial Planning
105 | Prepare advertisement for the 2025/2026 OR and AR to be released for information which must be placed on the municipal website within five (5) days after it is approved | MFMA - Sec 129(3) |  |  |  |  | 17/03/2027 to 19/03/2027 | Financial Planning and Accounting Analyst / Administrative Support Officer
106 | Ensure that the 2025/2026 OR and AR be made available at all municipal offices and libraries for information | MFMA - Sec 129(3) |  |  |  |  | 31/03/2027 to 02/04/2027 | Financial Planning and Accounting Analyst / Administrative Support Officer
107 | Submit the Annual Report and Oversight Report to the provincial legislature as per circular | MFMA - Sec 132(1) & (2) |  |  |  |  | 31/03/2027 to 02/04/2027 | Financial Planning and Accounting Analyst / Administrative Support Officer
108 | Submit the Draft IDP, SDBIP, SDF and Budget to Department of Local Government, National and Provincial Treasury, prescribed national or provincial organs of state and to other municipalities affected by the IDP and budget | MFMA - Sec 22(b) MSA - Sec 32(1) MBRR - Reg 20 | Immediately | Immediately | Immediately | Immediately |  | Manager: IDP/R&D and Manager: Budget Control and Cost Accounting, Manager: Spatial Planning
109 | Public Open Days to consult the Draft IDP, SDBIP, and Budget | MFMA - Sec 22(a) MSA - Sec 21A MPPMR - Reg 15(3) | 05/04/2027 to 29/04/2027 | 05/04/2027 to 29/04/2027 | 05/04/2027 to 29/04/2027 |  |  | Manager: IDP/R&D Manager: Budget Control and Cost Accounting
110 | Quarter 3 (2026/2027) Performance Assessments for City Manager, Executive Directors and Reporting Level 3 Managers | MPPMR - Reg 13 GN 21- 17/01/2014 |  |  | 15/04/2027 - 16/04/2027 |  |  | Head: Strategic Performance Management and M&E
111 | Annual Performance Assessments for City Manager, Executive Directors and Reporting Level 3 Managers (Period 2025/2026 Financial Year) | MPPMR - Reg 13 GN 21- 17/01/2014 |  |  | 03/09/2027 |  |  | Head: Strategic Performance Management and M&E
112 | Submit Monthly Report on the Budget for period ending 31 March 2027 within 10 working days to Executive Mayor | MFMA Section 71(1) |  |  |  |  | 14/04/2027 | Manager: Financial Statements, Reporting and Cash Management
113 | Submit Third Quarter Performance Report to Executive Mayor and Mayoral Committee | MPPMR - Reg 13 |  |  | 21/04/2027 |  |  | Head: Strategic Performance Management and M&E
114 | Submit Third Quarter Performance Report to Council | MPPMR - Reg 13 |  |  | 28/04/2027 |  |  | Head: Strategic Performance Management and M&E
115 | Submit Quarterly Report for period ending 31/03/2027 on implementation of the Budget and financial state of affairs of the municipality to Council | MFMA - Sec 52(d) MFMA - Sec 71(1) MBRR - Reg 29 |  |  |  |  | 28/04/2027 | Manager: Financial Statements, Reporting and Cash Management
116 | Submit 3rd Quarter 2026/27 Performance Reports - SDBIP and Performance Reports to National and Provincial Treasury | MPPMR - Reg 13 |  |  | 29/04/2027 |  |  | Head: Strategic Performance Management and M&E
117 | Place 2026/2027 Third Quarter Performance Report on website | MFMA - Sec 75(2) MSA - Sec 21(b) |  |  | 29/04/2026 |  |  | Head: Strategic Performance Management and M&E
MAY 2027
118 | Draft IDP - Alignment after April feedback for May |  | 04/05/27 - 15/05/27 |  |  |  |  | Manager: IDP/R&D
119 | SIME - IDP and Budget Assessments by Provincial Treasury and Department of Local Government | MSA Chapter 5 MFMA | 13/05/2027 |  |  |  |  | Manager: IDP/R&D, Manager: Budget Control and Cost Accounting
120 | Submit Monthly Report on the Budget for period ending 30/04/2027 within 10 working days to Executive Mayor | MFMA Section 71(1) |  |  |  |  | 14/05/2027 | Manager: Financial Statements, Reporting and Cash Management
121 | Consider the comments from the Intergivernmental Steering Committee and finalise the final draft SDF | DBMLUP - Sec 6(6) |  |  |  | 14/05/2027 |  | Manager: Spatial Planning
122 | Budget Steering Committee considers submissions made by the Local Community, National or Provincial Treasury, National or Provincial Organs of State or Municipalities (B-Municipalities) | MFMA - Sec 23 | 2027-12-05 | 2027-12-05 |  | 2027-12-05 |  | Manager: IDP/R&D and Manager: Budget Control and Cost Accounting, Manager: Spatial Planning
123 | Final Budget captured and approved on Budget Management Module (BMM) |  |  | 18/05/2027 |  |  |  | Manager: Budget Control and Cost Accounting
124 | Finance Portfolio Committee considers submissions made by the Local Community, National or Provincial Treasury, National or Provincial Organs of State or Municipalities (B-Municipalities) and recommends Final Budget to MAYCO | MFMA - Sec 24 |  | 19/05/2027 |  |  |  | Manager: Budget Control and Cost Accounting
125 | MAYCO meeting to approve Amended IDP, Performance Management Information and targets as well as the Budget (at least 30 days before the start of the budget year), and Drakenstein Spatial Development Framework | MFMA - Sec 24 | 21/05/2027 | 21/05/2027 | 21/05/2027 | 19/05/2027 |  | Manager: IDP/R&D and Manager: Budget Control and Cost Accounting, Manager: Spatial Planning
126 | Council meeting to adopt Amended IDP, Performance Management Information and Targets as well as the Budget (at least 30 days before the start of the budget year), and Drakenstein Spatial Development Framework | MFMA - Sec 24 DBMLUP - Sec 6(8) | 26/05/2027 | 26/05/2027 | 26/05/2027 | 26/05/2027 |  | Manager: IDP/R&D and Manager: Budget Control and Cost Accounting, Manager: Spatial Planning
JUNE 2027
127 | Place the IDP, Multi-Year Budget, all Budget-Related documents and all Budget-Related Policies, and Drakenstein Spatial Development Framework on the website | MFMA - Sec 22 and 75 MSA - Sec 21A and 21B | 02/06/2027 | 02/06/2027 |  | 02/06/2027 |  | Manager: IDP/R&D Manager: Budget Control and Cost Accounting Manager: Spatial Planning
128 | Submit a copy of the Amended IDP and Drakenstein Spatial Development Framework to the MEC for LG (within 10 days of the adoption of the plan) | MSA - Section 32 LUPA - Section 14 | 03/06/2027 |  |  | 03/06/2027 |  | Manager: IDP/R&D Manager: Spatial Planning
129 | Give notice to the public of the adoption of the IDP, SDF and Budget (within 14 days of the adoption of the plan) and budget (within 10 working days) | MBRR - Reg 18 MSA - Sec 25(4)(a)(b) | 03/06/2027 |  |  | 03/06/2027 |  | Manager: IDP/R&D Manager: Budget Control and Cost Accounting Manager: Spatial Planning
130 | Give notice of the adoption of the SDF in the Provincial Gazette | SPLUMA - Sec 20(1) DBMLUP - Sec 6(8) |  |  |  | 03/06/2027 |  | Manager: Spatial Planning
131 | Submit approved budget to National and Provincial Treasuries (both printed and electronic formats) | MFMA - Sec 24(3) MBRR - Reg 20 |  | 2027-11-06 |  |  |  | Manager: Budget Control and Cost Accounting
132 | Submit to the Executive Mayor the SDBIP for the Budget Year (no later than 14 days after the approval of an annual budget) | MFMA - Sec 69(3)(a) |  |  | 11/06/2027 |  |  | Head: Strategic Performance Management and M&E
133 | Submit Monthly Report on the Budget for period ending 31/05/2027 within 10 working days to Mayor | MFMA Section 71(1) |  |  |  |  | 14/06/2027 | Manager: Financial Statements, Reporting and Cash Management
134 | Executive Mayor takes all reasonable steps to ensure that the SDBIP is approved (within 28 days after Approval of the Budget) | MFMA - Sec 53(1)(c) (ii) |  |  | 28/06/2027 |  |  | Head: Strategic Performance Management and M&E
135 | Submit certification that the annual budget is locked on the municipality's financial system | MFMA - Section 74 |  | 30/06/2027 |  |  |  | Manager: Budget Control and Cost Accounting
JULY 2027
136 | Make public the projections, targets and indicators as set out in the SDBIP (no later than 14 days after the approval of the SDBIP) and submit to National and Provincial Treasuries (no later than 10 working days after the approval of the SDBIP) | MFMA Section 53(3)(a MBRR Reg 19 |  |  | 30/07/2027 |  |  | Head: Strategic Performance Management and M&E
129 | Make public the performance agreements of City Manager and Executive Directors (no later than 14 days after the approval of the SDBIP) | MFMA Section 53(3)(b): |  |  | 30/07-2026 - 30/07/2026 |  |  | Head: Strategic Performance Management and M&E